## Slide 1
SOFTWARE PROJECT MANAGEMENT

## Slide 2
Software Project Planning

## Slide 3: Software Project Planning (Recap)
Initiation and approval of the project typically happens at the end of the Feasibility study
Planning is one of the first tasks in the project where the Project Manager focusses on what needs to be achieved and how.
Planning involves looking ahead and making provisions for the required resources so that the project will be executed smoothly without surprises
The outcome of the planning phase would typically be a Project Plan
  The level of this project plan would depend on the nature of the project whether it is a exploratory, research or development etc.
  The project plan can evolves over the lifecycle of the project based on the progress achieved, changes in context, risks encountered or any unforeseen changes.
Monitoring Execution & Control

## Slide 4: A Project plan needs to answer questions from
Sponsors Perspective like
  Where does this product/project fit strategically to the vision/roadmap of the organization
  What is the investment (Budget) / Revenue expected (Predicted)
  How long will this take to build and what are the risks
  Who is responsible and how is the progress tracked
  What resources are required and what are the deliverables
  How will we say that the project is Complete/successful/has met exit criteria.
  Customer perspective
  Does the team working on the product/project understand the problem
  How long will it take, how much will it cost
  Criteria for accepting the product/project to be complete and meeting expectations

## Slide 5: Project plan needs to answer questions from -
Execution Stakeholders perspective
  What Lifecycle are we going to follow
  Criteria for prioritizing of requirements
  Project Organization:
    Relationships to other parts of the organization (Upstream/Downstream)
    Roles of people
    User involvement
  Standards-Guidelines-Procedures to be followed
  Communication Mechanisms
  Schedule with Detailed Work Breakdown and Ownership

## Slide 6: Project planning process (Recap)

## Slide 7: Software Project Planning Steps
Understanding the expected deliverables of the project
    Expectations of customers, stakeholders in terms of the deliverables
    The market forces driving the project (technology/ competition etc.)
    Looking at the high level decisions of Make-Buy-Reuse
  This is typically supported by the results of the feasibility study and the requirements elicited.

## Slide 8: Software Project Planning Steps
Planning the process
  Choice of the lifecycle can be based on
  Generics on project/product characteristics which can be used to help on the choice of the lifecycle in terms of the activities, goals, time boundedness, inter-related activities and constraints on scope, time and other resources
  We can also characterize it based on the degree of certainty as High or Low of
    Product
    Process
    Resource

## Slide 9: Software Project Planning Steps

## Slide 10: Software Project Planning Steps
  Models, Standards, guidelines, procedures
  What processes model and procedures are to be followed?
  What standards should this conform to? Technical, Interoperability, Quality, Regulatory etc.
  Configuration Management, Change management, Quality Plans
  Identifying the tools that needs to be used through the lifecycle

## Slide 11: Software Project Planning Steps
Organize the project
Structure:
    Organizational Structure in terms of people, team, responsibilities E.g. Project Manager, Programmer, Architects, Engineers etc.
    Context of Hierarchical, Flat, Functional, Matrix, Line Organizations
Partners :
    Identification of eco-system partners for the project Build, Install, Localization, Documentation, Product Management, Product marketing, Sales, Pre-Sales, Support etc.
    Relationship of Partners – Upstream and Downstream

## Slide 12: Software Project Planning Steps
Determining Deliverables
Buy vs. Develop vs. Reuse
WBS
  Typically its an iterative process
  Considering the requirements and in discussion with a few key team members, Split project into Level 1 - Tasks/Activities or subprojects
  Decompose these into more detailed tasks/ Activities (Level 2) … and do this till you believe you have enough granularity in the tasks which can be meaningfully tracked
  This hierarchical tree structure is called Work breakdown structure or WBS

## Slide 13: Software Project Planning Steps
WBS (Cont.)
  Aggregate these tasks into Phases
  Identification of Milestones/Checkpoints/ Toll Gates for these Phases/Tasks
  Entry Criteria & Exit criteria for the phases/ milestones/ check points
  Identification of Work Packages for final product
    Estimation of the Tasks/Activities (effort and time)
  Estimation is typically done for effort needed for executing each of the tasks in the WBS
  WBS itself is an estimation of all the tasks involved in the project, there can be estimate for cost ..etc.
  Estimation can be done top down or bottoms up

## Slide 14: Software Estimation approaches
Estimation could be
Experience based like based Delphi, Modified Delphi, Expert judgement, comparative studies
Formal techniques based like the formula based CoCoMo for project effort, where the formula is based on historical estimates of product attributes, such as size, and process characteristics and experience of staff involved E.g.
In CoCoMo (Constructive Cost Model), projects are categorized into organic, embedded and semi detached.
  Organic : Team size is small, problem is well understood, people have experience of solving it earlier.
  Embedded : Large team size, complex, need people with sufficient experience
  Semi-detached : In between these two

## Slide 15: Estimation Approaches
  and
  Effort E = ab(KLOC)b Person months, Where
  Similarly there is an formula for Schedule.
  Types of CoCoMo models
  Basic – for quick rough calculations
  Intermediate takes cost drivers into consideration
  Detailed in addition factors in dependencies

## Slide 16: Software Project Planning Steps
  Scheduling and allocating resources
  Schedule is created using outcomes of WBS & estimation, and is the calendarization of the work activities
  Involves bringing all concerned individuals to participate in building this schedule
  Identification and allocation of the resources to the broken down project activities (WBS).
    Hardware, Software, Human
    Rework on estimates and schedule based on their competencies/lack of competencies
  Validation of upstream and downstream dependencies for these Tasks/Phases

## Slide 17: Software Project Planning Steps
  Scheduling and allocating resources (Contd.)
  Organizing tasks concurrently to make optimal use of people working on the project and sequentially to manage dependencies
  Use of graphical tools like Gantt chart to visualize these
  Identification of schedule risks and mitigation plans
  Minimize task dependencies to avoid delays caused by one task waiting for another to complete
  Taking care of working conditions such as holidays, work shifts, resource availability and so on
  Involves multiple iterations of looking at Feature requirements- Schedule/Calendar - Resource/people and costs
  Costing in terms of Budget, Capital and Expenses
  Tools like the Microsoft project are used for scheduling
Gantt Chart

## Slide 18
View of what you would see with a tool like Microsoft Project :
Gantt Chart .. WBS, Schedule, Dependencies etc

## Slide 19: Software Project Planning Steps
  Identifying and Managing risks
  Risk is any unexpected event that might affect the people, processes, technology, and resources involved.
  Risk Management can be for Products, Projects, Organizations etc.

## Slide 20: Software Project Planning Steps
  Steps involved in Risk Management
  Identification of the Risk (what might go wrong)
  Assessment and analysis (assessment of probability of occurrence and impact)
  Mitigation/Fall back planning (what can we do about it? What might we have to do)
  Identification and Catching the Trigger (how will we know the risk has happened)
  Execution and monitoring of the Mitigation Plan
Mitigation Planning

## Slide 21: Software Project Planning Steps
  Developing a quality management process
    Plans for Tracking of the projects/product progress
    Communication plans (Verbal/Written)
    Quality assurance plans (including all processes planned
    Test Completion criteria’s
    Early verification or Customer validation e.g. Beta

## Slide 22: Software Project Planning Steps
  Plans for tracking Project Plan & Delivery plan
    Plans for Managing the Project Plan
    Procedures to be followed to release the product to customer
  Independently there would be activities towards
    Staffing and people engagement/ performance management activities
    Compensation and Benefits management

## Slide 23: Outcome & Role
  The out come of the list of activities done as part of the planning would be
    Project Plan
    Work Breakdown – List of Tasks in a granular form
    Schedule – Calendarized plan for implementation and delivery
    Resource Management – Allocation, Balancing of workload, orchestration for parallelism/sequencing for efficiency and dependency management, defining of roles and responsibilities
    Plans for communication, metrics, checkpoints, criteria’s for completion etc.
    Risk management Plan, Quality Plan – SQA ..
  Roles in Project Management
      Project Manager .. Different levels
      Program Management ..